## GANTT PLANNED
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total PM - Partner | [10 empty] | VENDOR
Job ID | WP | Mod.nº | Module Name | APP | AO | Molecule | 6: 2020; 1: 2021; 1: 2022; 1: 2023 | 2.IPP | 3.UNIZAR | 4.IPL | 6.FZB | 7.IM4TB | 15.UHC | 16.UNIPD | 17.UNIPV | 20. SCI | 22.BAR | 23.QPS | WuXi | Covance | Aptuit | QPS | Sequani | Ardena Oss | Beneficiary/Provider | PM | Months
| WP2 | 1 | In vitro activity against Mycobacterium tuberculosis
TBA587-APP2-M1.1-UNIZAR | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) | APP2 | TBA | 587 | [44 empty] | 9 | [15 empty] | 3.UNIZAR | 9 | 9 | bar: 10 to 6
TBA587-APP2-M1.1-UNIPV | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) | APP2 | TBA | 587 | [50 empty] | 2 | [9 empty] | 17.UNIPV | 2 | 4 | bar: 9 to 12
GSK286-APP2-M1.1-UNIZAR | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) | APP2 | GSK | 286 | [44 empty] | 3 | [15 empty] | 3.UNIZAR | 3 | 6 | bar: 1 to 6
GSK839-APP3-M1.1-IPL | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) | APP3 | GSK | 839 | [45 empty] | 1 | [14 empty] | 4.IPL | 1 | 3 | bar: 11 to 1
MPL447-APP1-M1.1-IPL-01 | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) - Action 4 | APP1 | MPL | 447 | [45 empty] | 0.66667 | [14 empty] | 4.IPL | 0.66667 | 3 | bar: 1 to 3
MPL447-APP1-M1.1-IPL-02 | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) - Action 5 | APP1 | MPL | 447 | [45 empty] | 0.66667 | [14 empty] | 4.IPL | 0.66667 | 3 | bar: 1 to 3
MPL447-APP1-M1.1-UNIZAR | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) - Action 6 | APP1 | MPL | 447 | [44 empty] | 1.5 | [15 empty] | 3.UNIZAR | 1.5 | 4 | bar: 1 to 4
DDU209-APP3-M1.1-IPL | WP2 | 1.1 | Standard Extracellular assays (capacity n > 1000) - Action 6 | APP3 | DDU | 209 | [60 empty] | 4.IPL | 2 | 3 | bar: 5 to 7
GSK286-APP2-M1.2-UHC | WP2 | 1.2 | Intracellular assays | APP2 | GSK | 286 | [48 empty] | 4 | [11 empty] | 15.UHC | 4 | 4 | bar: 11 to 2
MPL447-APP1-M1.3.2-UNIPD | WP2 | 1.3.2 | Alternative in vitro assays - Ex vivo human model of infection based on Granuloma Like Structures (GLSs) | APP1 | MPL | 447 | [49 empty] | 1.5 | [10 empty] | 16.UNIPD | 1.5 | 3 | bar: 1 to 3
TBA587-APP2-M1.3.2-UNIPD | WP2 | 1.3.2 | Alternative in vitro assays - Ex vivo human model of infection based on Granuloma Like Structures (GLSs) | APP2 | TBA | 587 | [49 empty] | 12 | [10 empty] | 16.UNIPD | 12 | 13 | bar: 10 to 10
MPL447-APP1-M1.3.3-UHC | WP2 | 1.3.3 | Alternative in vitro assays - Artificial Caseum Assay (ACA) | APP1 | MPL | 447 | [48 empty] | 4 | [11 empty] | 15.UHC | 4 | 2 | bar: 1 to 2
MPL447-APP1-M1.3.3-IPL | WP2 | 1.3.3 | Alternative in vitro assays - Artificial Caseum Assay (ACA) | APP1 | MPL | 447 | [60 empty] | 4.IPL | 1 | 2 | bar: 1 to 2
TBA587-APP2-M1.3.4-UNIZAR | WP2 | 1.3.4 | Alternative in vitro assays - Hollow Fber system for TB (HFS-TB) | APP2 | TBA | 587 | [44 empty] | 9 | [15 empty] | 3.UNIZAR | 9 | 9 | bar: 7 to 3
GSK286-APP2-M1.3.4-UNIZAR | WP2 | 1.3.4 | Alternative in vitro assays - Hollow Fber system for TB (HFS-TB) | APP2 | GSK | 286 | [44 empty] | 6 | [15 empty] | 3.UNIZAR | 6 | 6 | bar: 7 to 12
MPL447-APP1-M1.3.4-UNIZAR | WP2 | 1.3.4 | Alternative in vitro assays - Hollow Fber system for TB (HFS-TB) | APP1 | MPL | 447 | [44 empty] | 6 | [15 empty] | 3.UNIZAR | 6 | 6 | bar: 7 to 12
TBA587-APP3-M1-FZB | WP2 | 1 | In vitro activity against Mycobacterium tuberculosis | APP3 | TBA | 587 | [60 empty] | 6.FZB | 6.75 | 9 | bar: 4 to 12
TBA587-APP3-M1-UNIZAR | WP2 | 1 | In vitro activity against Mycobacterium tuberculosis | APP3 | TBA | 587 | [60 empty] | 3.UNIZAR | 0.25 | 3 | bar: 5 to 7
| WP2 | T | TOTAL ACTIVITY MODULE 1 |  |  |  | 0 | 0 | 0 | 1 | 3 | 5 | 5 | 11 | 10 | 7 | 5 | 6 | 6 | 5 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 34.5 | 2.3333 | 0 | 0 | 8 | 13.5 | 2 | 0 | 0 | 0 | [6 empty] | SUBTOTAL
| WP2 | 2 | Mutation Rate
TBA587-APP2-M2.1-UNIPV | WP2 | 2.1 | Frequency of Resistance assays | APP2 | TBA | 587 | [50 empty] | 5 | [9 empty] | 17.UNIPV | 5 | 10 | bar: 9 to 6
TBA587-APP2-M2.1-IPL | WP2 | 2.1 | Frequency of Resistance assays | APP2 | TBA | 587 | [45 empty] | 3 | [14 empty] | 4.IPL | 3 | 6 | bar: 9 to 2
DDU209-APP3-M2.1-IPP | WP2 | 2.1 | Frequency of Resistance assays | APP3 | DDU | 209 | [60 empty] | 2.IPP | 3 | 6 | bar: 5 to 10
MPL447-APP1-M2.1.1-IPP | WP2 | 2.1.1 | Frequency of Resistance assays - Standard in vitro fluctuation analysis (FA) | APP1 | MPL | 447 | [43 empty] | 6 | [16 empty] | 2.IPP | 6 | 3 | bar: 1 to 3
| WP2 | T | TOTAL ACTIVITY MODULE 2 |  |  |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | [6 empty] | SUBTOTAL
| WP2 | 3 | MDR/XDR
MPL447-APP2-M3.1-FZB | WP2 | 3.1 | Standard Extracellular assays | APP2 | MPL | 447 | [46 empty] | 6.75 | [13 empty] | 6.FZB | 6.75 | 9 | bar: 2 to 10
MPL447-APP2-M3,1-UNIZAR | WP2 | 3.1 | Standard Extracellular assays | APP2 | MPL | 447 | [44 empty] | 0.75 | [15 empty] | 3.UNIZAR | 0.75 | 3 | bar: 3 to 5
| WP2 | T | TOTAL ACTIVITY MODULE 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 6.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SUBTOTAL
| WP2 | 4 | MoA
TBA587-APP2-M4.1-BAR | WP2 | 4.1 | Omics technologies | APP2 | TBA | 587 | [52 empty] | 6 | [7 empty] | 22.BAR | 6 | 12 | bar: 1 to 12
GSK286-APP2-M4.1-BAR | WP2 | 4.1 | Omics technologies | APP2 | GSK | 286 | [52 empty] | 1.41 | [7 empty] | 22.BAR | 1.41 | 6 | bar: 5 to 10
MPL447-APP1-M4.1-BAR-01 | WP2 | 4.1 | Omics technologies - Action 8 | APP1 | MPL | 447 | [52 empty] | 1.91 | [7 empty] | 22.BAR | 1.91 | 6 | bar: 5 to 10
MPL447-APP1-M4.1-BAR-02 | WP2 | 4.1 | Omics technologies - Action 10 | APP1 | MPL | 447 | [52 empty] | 2.65 | [7 empty] | 22.BAR | 2.65 | 6 | bar: 5 to 10
DDU209-APP3-M4.1-IPP | WP2 | 4.1 | Omics technologies | APP3 | DDU | 209 | [60 empty] | 2.IPP | 3 | 6 | bar: 5 to 10
TBA587-APP2-M4.2-FZB | WP2 | 4.2 | Drug resistance, genomics & evolution assays | APP2 | TBA | 587 | [46 empty] | 11 | [13 empty] | 6.FZB | 11 | 11 | bar: 8 to 6
GSK286-APP2-M4.2-IPL | WP2 | 4.2 | Drug resistance, genomics & evolution assays | APP2 | GSK | 286 | [45 empty] | 3 | [14 empty] | 4.IPL | 3 | 4 | bar: 11 to 2
GSK286-APP2-M4.2-UNIPV | WP2 | 4.2 | Drug resistance, genomics & evolution assays | APP2 | GSK | 286 | [50 empty] | 6 | [9 empty] | 17.UNIPV | 6 | 12 | bar: 1 to 12
MPL447-APP1-M4.2-UNIPV | WP2 | 4.2 | Drug resistance, genomics & evolution assays | APP1 | MPL | 447 | [50 empty] | 1 | [9 empty] | 17.UNIPV | 1 | 12 | bar: 1 to 12
DDU209-APP3-M4.2-FZB | WP2 | 4.2 | Drug resistance, genomics & evolution assays | APP3 | DDU | 209 | [60 empty] | 6.FZB | 3.6 | 9 | bar: 5 to 1
| WP2 | 4.3 | Molecular biology & biochemistry
MPL447-APP1-M4.3.1-UNIPD | WP2 | 4.3.1 | Molecular biology & biochemistry - Molecular biology | APP1 | MPL | 447 | [49 empty] | 2 | [10 empty] | 16.UNIPD | 2 | 9 | bar: 1 to 9
MPL447-APP1-M4.3.1-UNIPV | WP2 | 4.3.1 | Molecular biology & biochemistry - Molecular biology | APP1 | MPL | 447 | [50 empty] | 2 | [9 empty] | 17.UNIPV | 2 | 9 | bar: 1 to 9
GSK839-APP3-M4.3.2-UNIPV | WP2 | 4.3.2 | Molecular biology & biochemistry - Biochemistry | APP3 | GSK | 839 | [50 empty] | 10 | [9 empty] | 17.UNIPV | 10 | 12 | bar: 1 to 12
MPL447-APP1-M4.3.2-UNIPV | WP2 | 4.3.2 | Molecular biology & biochemistry - Biochemistry - Action 12 | APP1 | MPL | 447 | [50 empty] | 2 | [9 empty] | 17.UNIPV | 2 | 4 | bar: 1 to 4
MPL447-APP1-M4.3.2-IPL | WP2 | 4.3.2 | Molecular biology & biochemistry - Biochemistry - Action 13 | APP1 | MPL | 447 | [45 empty] | 0.66667 | [14 empty] | 4.IPL | 0.66667 | 3 | bar: 1 to 3
| WP2 | 4.4 | MOA for HPI/virulence assays
| WP2 | T | TOTAL ACTIVITY MODULE 4 |  |  |  | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 9 | 9 | 8 | 7 | 11 | 11 | 10 | 10 | 10 | 8 | 4 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6667 | 11 | 0 | 0 | 2 | 21 | 0 | 11.97 | 0 | [6 empty] | SUBTOTAL
| WP3 | 5 | In vivo activity against M.tb
MPL447-APP3-M5-EUROFINS | WP3 | 5 | In vivo activity against M.tb | APP3 | TBA | MPL447 | [60 empty] | EUROFINS | 0 | 3 | bar: 7 to 9
MPL447-APP1-M5.1- SCI | WP3 | 5.1 | A 1-2 log reduction in Chronic and Acute BALB/c models, respectively, at non-toxic dosing (Action 1. Acute dose ranging study in BALB/c mice) | APP1 | MPL | 447 | [51 empty] | 4 | [8 empty] | 20. SCI | 4 | 2 | bar: 11 to 12
MPL447-APP1-M5.1-IPP | WP3 | 5.1 | A 1-2 log reduction in Chronic and Acute BALB/c models, respectively, at non-toxic dosing (Action 2. Chronic dose ranging study in BALB/c mice) | APP1 | MPL | 447 | [43 empty] | 6 | [16 empty] | 2.IPP | 6 | 3 | bar: 12 to 2
MPL447-APP1-M5.1-FZB | WP3 | 5.1 | A 1-2 log reduction in Chronic and Acute BALB/c models, respectively, at non-toxic dosing (Action 3. Chronic dose ranging study in C3HeB/FeJ mice) | APP1 | MPL | 447 | [46 empty] | 6 | [13 empty] | 6.FZB | 6 | 3 | bar: 2 to 4
| WP3 | 5.1 | Other mouse models
| WP3 | 5.1 | Biomarkers
| WP3 | T | TOTAL ACTIVITY MODULE 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | [6 empty] | SUBTOTAL
| WP3 | 6 | In vitro / in vivo PK
| WP3 | 6.1 | In vitro intrinsic clearance to give confidence in a human efficacious dose (<1000 mg efficacious dose)
| WP3 | 6.2 | Evidence supporting lack of reactive metabolites
| WP3 | 6.3 | PK parameters determined in at least one rodent and one non-rodent animal
| WP3 | 6.4 | Bioavailability of >30% using solid form and a suitable formulation to support safety studies
| WP3 | T | TOTAL ACTIVITY MODULE 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SUBTOTAL
MPL447-APP1-M7-Ardena Oss | WP6 | 7 | Pharma Development | APP1 | MPL | 447 | [47 empty] | X | [11 empty] | X | Ardena Oss |  | 2 | bar: 12 to 1
DDU209-APP2-M7.1- IOS | WP6 | 7.1 | API - Lead Optimisation (e.g. Route scouting, salt screen (polymorph, solubility, stability), physical stability (incl. forced deg.) | APP2 | DDU | 209 | [60 empty] | 21. IOS | 25 | 12 | bar: 3 to 2
MPL447-APP3-M8-EUROFINS | WP6 | 8 | In vitro tox (non-GLP) | APP3 | TBA | MPL447 | [60 empty] | EUROFINS | 0 | 2 | bar: 7 to 8
DDU209-APP1-M9-Charles River France | WP6 | 9 | In vivo tox (non-GLP) | APP1 | DDU | 209 | [47 empty] | X | [10 empty] | X |  | Charles River France |  | 4 | bar: 12 to 3
DDU384-APP1-M9-Sequani | WP6 | 9 | In vivo tox (non-GLP) | APP1 | DDU | 384 | [47 empty] | X | [10 empty] | X |  | Sequani |  | 4 | bar: 12 to 3
MPL447-APP1-M9-Charles River France | WP6 | 9 | In vivo tox (non-GLP) | APP1 | MPL | 447 | [47 empty] | X | [8 empty] | X |  |  |  | Charles River France |  | 7 | bar: 11 to 5
| WP6 | 9.1 | Formulation development for Toxicology in support to GLP Tox
| WP6 | 9.2 | MTD/DRF in rodent
| WP6 | 9.3 | Additional tox. studies depending on each molecule
MPL447-APP1-M10-Ardena Oss | WP6 | 10 | CMC: API (Non-GMP) | APP1 | MPL | 447 | [47 empty] | X | [11 empty] | X | Ardena Oss |  | 11 | bar: 1 to 11
| WP6 | 10.1 | Resynthesis API
| WP6 | 10.1 | API-Process Development
| WP6 | 10.1 | API-Phase I/II analytical program
| WP6 | 10.1 | Development Stability Studies
| WP6 | 10.1 | Scale up API-0.5/1kg non-GMP manufacture (for use in tox program/formulation development)
| WP6 | 10.1 | API-PGI assessment
| WP6 | 11 | API (GMP)
GSK839-APP1-M11.1-WuXi | WP6 | 11.1 | API-1kg API cGMP manufacture | APP1 | GSK | 839 | [47 empty] | X | [6 empty] | X | [5 empty] | WuXi |  | 6 | bar: 6 to 11
| WP6 | 11.1 | API-Development for scale-up of API (pilot plant manufacture)
| WP6 | 11.1 | API-Large scale synthesis of API (5-10kg)
| WP6 | 11.1 | API-raw material procurement (10kg) (halfway through dev program)
| WP6 | 11.1 | API-analytical method re-development/validation
| WP6 | 11.1 | API-stability study for large scale batch
| WP6 | 11.1 | API-Particle size control (incl potential micronisation)
| WP6 | 11.1 | API-Impurity/degradant identification
| WP6 | 11.1 | API-Impurity/degradant synthesis (as required)
| WP6 | 11.1 | API-analytical re-tests after 1 year non GMP
| WP6 | 12 | In vitro DMPK (GLP) [2]
| WP6 | 12.1 | Route and Synthesis of Radio or Stable Labelled Compound
| WP6 | 12.2 | ADME profiling + in vitro DDI risk assessment
| WP6 | 12.3 | Non-Rodent PK study
| WP6 | 12.4 | DMPK to support 2 species
| WP6 | 12.5 | In vitro Metabolism- Cross species comparison
GSK839-APP2-M13-Covance | WP6 | 13 | In vitro Tox (GLP) | APP2 | GSK | 839 | [47 empty] | X | [7 empty] | x |  |  |  |  | Covance | 0 | 7 | bar: 10 to 4
| WP6 | 13.1 | hERG Assay
| WP6 | 13.1 | Ames Assay
| WP6 | 13.1 | Lymphoma Mouse Study (MLA) (or HLPA)
| WP6 | 13.2 | GLP tox bioanalysis: Bioassay & dose/formulation analysis method development/validation, dose stability
GSK839-APP2-M14-Aptuit | WP6 | 14 | In vivo Tox (GLP) Rats | APP2 | GSK | 839 | [60 empty] | Aptuit | 0 | 7 | bar: 10 to 4
GSK286-APP3-M14-Covance-01 | WP6 | 14 | In vivo Tox (GLP) Rats | APP3 | GSK | GSK286 | [60 empty] | Covance | 0 | 10 | bar: 6 to 3
GSK839-APP2-M14-Covance | WP6 | 14 | In vivo Tox (GLP) Minipigs | APP2 | GSK | 839 | [47 empty] | X | [7 empty] | x |  |  |  |  | Covance | 0 | 6 | bar: 1 to 6
GSK286-APP3-M14-Covance-02 | WP6 | 14 | In vivo Tox (GLP) Cyno | APP3 | GSK | GSK286 | [60 empty] | Covance | 0 | 10 | bar: 6 to 3
| WP6 | 14.1 | CNS (Irwin rat) Study
| WP6 | 14.2 | Respiratory (rat)
| WP6 | 14.3 | Cardiovascular Non-Rodent | [50 empty] | X | [7 empty] | x
| WP6 | 14.4 | Non rodent DRF
| WP6 | 14.5 | 14- or 28-day Repeat dose
| WP6 | 14.6 | GLP tox bioanalysis: Bioassay & dose/formulation analysis method development/validation, dose stability
GSK839-APP2-M15-Aptuit | WP6 | 15 | CMC: Clinical Process Development (DP) | APP2 | GSK | 839 | [47 empty] | X | [8 empty] | x |  |  |  | Aptuit | 0 | 6 | bar: 2 to 7
| WP6 | 15.1 | Phase 1 Formulation and Analytical Development
| WP6 | 15.2 | Clinical Trial Manufacture & Bulk Test - Release for PhI
| WP6 | 15.3 | Clinical Packaging and Supply- if required
| WP7 | 16 | Regulatory. CTA submission-Approval
| WP7 | 16.1 | Documentation preparation for IMPD and Protocol
GSK286-APP1-M17-QPS | WP7 | 17 | FTIH SAD+MAD | APP1 | GSK | 286 | [53 empty] | x | [6 empty] | 23.QPS | 0 | 34 | bar: 6 to 8
TBA587-APP1-M17-QPS | WP7 | 17 | FTIH SAD+MAD | APP1 | TBA | 587 | [53 empty] | x | [6 empty] | 23.QPS | 0 | 36 | bar: 6 to 10
TBA587-APP1-M17.1-QPS-01 | WP7 | 17.1 | Single ascending dose trial | APP1 | TBA | 587 | [53 empty] | x | [6 empty] | 23.QPS | 0 | 16 | bar: 11 to 2
TBA587-APP1-M17.1-QPS-02 | WP7 | 17.1 | Multiple ascending dose trial | APP1 | TBA | 587 | [53 empty] | x | [6 empty] | 23.QPS | 0 | 20 | bar: 3 to 10
| WP7 | 17.1 | Final Report FTIH
| WP7 | 17.2 | PK and PK-PD modelling (single drug and “combos”)
| WP7 | 18 | FTIH COMBOS
| WP7 | 18.1 | Drug-Drug interaction trial
| WP7 | 18.1 | Final Report FTIH
| WP7 | 18.2 | PK and PK-PD modelling
| WP4 | 19 | Imaging
| WP4 | 19.1 | Dynamic PK/PD single cell time-lapse microscopy for Mtb
| WP4 | 19.1.1 | Time-Lapse Microscopy
| WP4 | 19.1.2 | Optimal dosing strategy
| WP4 | 19.2 | MALDI-MS analysis of healthy or sterilized tissue
| WP4 | 19.2.1 | Pharmacokinetics - Drug and related metabolites biodistribution and quantification
| WP4 | 19.2.2 | Pharmacodynamics - Comparative analysis
| WP4 | 19.3 | PET/CT MICE
| WP4 | 19.3.1 | PET/CT implementation
| WP4 | 19.3.2 | Longitudinal study
| WP4 | 19.3.3 | Post-processing
BENCH1-M19.4-CEA | WP4 | 19.4 | BSL3 for PET/CT in TB infected NHP | BENCH1 | BENCH1 | BENCH1 | [60 empty] | 10.CEA |  | 9 | bar: 4 to 12
| WP4 | 19.4.1 | PK studies
BENCH2-M19.4.2-CEA | WP4 | 19.4.2 | Efficacy studies | BENCH2 | BENCH2 | BENCH2 | [60 empty] | 10.CEA |  | 9 | bar: 4 to 12
BENCH3-M19.4.2-PHE | WP4 | 19.4.2 | Efficacy studies | BENCH3 | BENCH3 | BENCH3 | [60 empty] | 13.PHE | 15 | 15 | bar: 7 to 9
| WP4 | 19.4.3 | Scan
| WP4 | 19.5 | Radiomics analysis
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Action 1 (Module 1.3.4). Prediction of the exposure-response in humans using preclinical data plus human PK in vitro PK/PD studies (HFS-TB) (UNIZAR). Timeline TBC but estimated on the second half of 2021
Note on BK107: Estefania Callado: Vendor amended
Note on BK111: Estefania Callado: Vendor amended
Note on M121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Specific timelines for SAD and MAD missing, so termination date TBC

## GANTT EXECUTED
[7 empty] | 2020 | [6 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
Job ID | WP | Mod.nº | Module Name | APP | AO | Molecule | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | Beneficiary/Provider | PM | Months | Original Start | Original End | Planned Start | Planned end | Start | End | Reporting | Start State | End state | Consumed Months | Completion Executed (%) | Completion Target (%) | Follow-up document
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| WP2 | 1 | Module 1
Job 1 | WP2 | 1.1 | Module 2 | APP2 | BAT | BAT587 | 10: 0; 11: 0; 12: 0; 1: 0; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 03.ZARA | 9 | 14 | 2020-10-01 | 2021-07-01 | 2021-02-01 | 2022-04-01 | 2021-02-01 |  |  | Late Start | Late End | 17 | 92.86% | 121.4% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=46
Job 2 | WP2 | 1.1 | Module 3 | APP2 | BAT | BAT587 | 9: 0; 10: 0; 11: 0; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1 |  | 17.PVT | 2 | 6 | 2020-09-01 | 2021-01-01 | 2020-12-01 | 2021-06-01 | 2020-12-01 | 2021-06-01 | SIGNED | Late Start | Late End | 18 | 250% | 300% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=45
Job 3 | WP2 | 1.1 | Module 4 | APP2 | KSG | KSG286 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1 |  | 03.ZARA | 3 | 6 | 2021-01-01 | 2021-07-01 | 2021-07-01 | 2022-01-01 | 2021-07-01 |  |  | Late Start | Late End | 14 | 133.3% | 233.3% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=44
Job 4 | WP2 | 1.1 | Module 5 | APP3 | KSG | KSG839 | 11: 0; 12: 0; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1 |  | 04.NBC | 1 | 6 | 2020-11-01 | 2021-02-01 | 2021-01-01 | 2021-07-01 | 2021-01-01 | 2021-06-30 | Ongoing | Late Start | Late End | 16 | 233.3% | 266.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=43
Job 5 | WP2 | 1.1 | Module 6 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 04.NBC | 0.66667 | 12 | 2021-01-01 | 2021-04-01 | 2021-04-01 | 2022-04-01 | 2021-04-01 |  |  | Late Start | Late End | 14 | 91.67% | 116.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=42
Job 6 | WP2 | 1.1 | Module 7 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 04.NBC | 0.66667 | 12 | 2021-01-01 | 2021-04-01 | 2021-04-01 | 2022-04-01 | 2021-04-01 |  |  | Late Start | Late End | 14 | 91.67% | 116.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=41
Job 7 | WP2 | 1.1 | Module 8 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1 |  | 03.ZARA | 1.5 | 9 | 2021-01-01 | 2021-05-01 | 2021-03-01 | 2021-12-01 | 2021-03-01 | 2021-12-01 | Ongoing | Late Start | Late End | 14 | 133.3% | 155.6% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=40
Job 8 | WP2 | 1.1 | Module 9 | APP3 | DDU | DDU209 | 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1 |  | 04.NBC | 2 | 7 | 2021-05-01 | 2021-08-01 | 2021-07-01 | 2022-02-01 | 2021-07-01 | 2022-01-15 |  | Late Start | Late End | 10 | 114.3% | 142.9% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=39
Job 9 | WP2 | 1.2 | Module 10 | APP2 | KSG | KSG286 | 11: 0; 12: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1 |  | 15.UHC | 4 | 6 | 2020-11-01 | 2021-03-01 | 2021-07-01 | 2022-01-01 | 2021-07-01 |  |  | Late Start | Late End | 16 | 133.3% | 266.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=38
Job 10 | WP2 | 1.1.3 | Module 11 | CPP1 | CPP1 | CPP1 | [44 empty] | 03.ZARA | 12 | 12 | 2021-12-01 | 2022-12-01 | 2021-12-01 | 2022-12-01 |  |  |  | On Time | On Time | 3 | 25% | 25% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=37 | bar: 12 to 11
Job 11 | WP2 | 1.1.3 | Module 12 | CPP1 | CPP1 | CPP1 | [44 empty] | 03.ZARA | 6 | 6 | 2022-02-01 | 2022-08-01 | 2022-02-01 | 2022-08-01 |  |  |  | On Time | On Time | 1 | 16.67% | 16.67% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=36 | bar: 2 to 7
Job 12 | WP2 | 1.1.3 | Module 13 | CPP1 | CPP1 | CPP1 | [44 empty] | 04.NBC | 12 | 6 | 2022-02-01 | 2022-08-01 | 2022-02-01 | 2022-08-01 |  |  |  | On Time | On Time | 1 | 16.67% | 16.67% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=35 | bar: 2 to 7
Job 13 | WP2 | 1.3.2 | Module 14 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: R |  | 16.PCP | 1.5 | 9 | 2021-01-01 | 2021-04-01 | 2021-05-01 | 2022-02-01 | 2021-05-01 | 2022-02-01 |  | Late Start | Late End | 14 | 111.1% | 155.6% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=34
Job 14 | WP2 | 1.3.2 | Module 15 | APP2 | BAT | BAT587 | 10: 0; 11: 0; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1 |  | 16.PCP | 12 | 15 | 2020-10-01 | 2021-11-01 | 2020-12-01 | 2022-03-01 | 2020-12-01 |  |  | Late Start | Late End | 17 | 100% | 113.3% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=33
Job 15 | WP2 | 1.3.3 | Module 16 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1 |  | 15.UHC | 4 | 5 | 2021-01-01 | 2021-03-01 | 2021-04-01 | 2021-09-01 | 2021-04-01 | 2021-09-01 | Ongoing | Late Start | Late End | 14 | 220% | 280% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=32
Job 16 | WP2 | 1.3.3 | Module 17 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1 |  | 04.NBC | 1 | 5 | 2021-01-01 | 2021-03-01 | 2021-04-01 | 2021-09-01 | 2021-04-01 | 2021-09-01 | Ongoing | Late Start | Late End | 14 | 220% | 280% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=31
Job 17 | WP2 | 1.3.4 | Module 18 | APP2 | BAT | BAT587 | [44 empty] | 03.ZARA | 9 | 9 | 2021-07-01 | 2022-04-01 | 2021-07-01 | 2022-04-01 |  |  |  | On Time | On Time | 8 | 88.89% | 88.89% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=30 | bar: 7 to 3
Job 18 | WP2 | 1.3.4 | Module 19 | APP2 | KSG | KSG286 | [44 empty] | 03.ZARA | 6 | 6 | 2022-07-01 | 2023-01-01 | 2022-07-01 | 2023-01-01 |  |  |  | On Time | On Time | 0 | 0% | 0% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=29 | bar: 7 to 12
Job 19 | WP2 | 1.3.4 | Module 20 | APP1 | BAT | CNN447 | [44 empty] | 03.ZARA | 6 | 6 | 2023-07-01 | 2024-01-01 | 2023-07-01 | 2024-01-01 |  |  |  | On Time | On Time | 0 | 0% | 0% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=28 | bar: 7 to 12
Job 20 | WP2 | 1 | Module 21 | APP3 | BAT | BAT587 | [44 empty] | 06.FZB | 6.75 | 11 | 2021-04-01 | 2022-01-01 | 2021-04-01 | 2022-03-01 | 2021-04-01 |  |  | On Time | Late End | 11 | 100% | 100% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=27 | bar: 4 to 2
Job 21 | WP2 | 1 | Module 22 | APP3 | BAT | BAT587 | [44 empty] | 03.ZARA | 0.25 | 10 | 2021-05-01 | 2021-08-01 | 2021-05-01 | 2022-03-01 | 2021-05-01 | 2021-11-17 | Ongoing | On Time | Late End | 10 | 100% | 100% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=26 | bar: 5 to 2
| WP2 | T | Module 23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 5 | 10 | 12 | 11 | 14 | 14 | 12 | 12 | 12 | 12 | 10 | 10 | 7 | 3 | 3 | 3 | 4 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 |  | SUBTOTAL | 100.3333 | 178
| WP2 | 2 | Module 24
Job 22 | WP2 | 2.1 | Module 25 | APP2 | BAT | BAT587 | 9: 0; 10: 0; 11: 0; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 17.PVT | 5 | 16 | 2020-09-01 | 2021-07-01 | 2020-12-01 | 2022-04-01 | 2020-12-01 |  |  | Late Start | Late End | 18 | 93.75% | 112.5% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=23
Job 23 | WP2 | 2.1 | Module 26 | APP2 | BAT | BAT587 | 9: 0; 10: 0; 11: 0; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1 |  | 04.NBC | 3 | 15 | 2020-09-01 | 2021-03-01 | 2020-12-01 | 2022-03-01 | 2020-12-01 |  |  | Late Start | Late End | 18 | 100% | 120% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=22
Job 24 | WP2 | 2.1 | Module 27 | APP3 | DDU | DDU209 | 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 02.PCW | 3 | 9 | 2021-05-01 | 2021-11-01 | 2021-07-01 | 2022-04-01 | 2021-07-01 |  |  | Late Start | Late End | 10 | 88.89% | 111.1% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=21
Job 25 | WP2 | 2.1.1 | Module 28 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 02.PCW | 6 | 13 | 2021-01-01 | 2021-04-01 | 2021-03-01 | 2022-01-01 | 2021-03-01 | 2022-01-01 |  | Late Start | Late End | 14 | 92.31% | 107.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=20
| WP2 | T | Module 29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SUBTOTAL | 17 | 53
| WP2 | 3 | Module 30
Job 26 | WP2 | 3.1 | Module 31 | APP2 | BAT | CNN447 | 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1 |  | 06.FZB | 6.75 | 9 | 2021-02-01 | 2021-11-01 | 2021-04-01 | 2022-01-01 | 2021-04-01 |  | ? | Late Start | Late End | 13 | 122.2% | 144.4% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=17
Job 27 | WP2 | 3.1 | Module 32 | APP2 | BAT | CNN447 | 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1 |  | 03.ZARA | 0.75 | 7 | 2021-03-01 | 2021-06-01 | 2021-05-01 | 2021-12-01 | 2021-05-01 | 2021-12-01 | Ongoing | Late Start | Late End | 12 | 142.9% | 171.4% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=16
| WP2 | T | Module 33 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SUBTOTAL | 7.5 | 16
| WP2 | 4 | Module 34
Job 28 | WP2 | 4.1 | Module 35 | APP2 | BAT | BAT587 | [44 empty] | 22.BAR | 6 | 13 | 2022-01-01 | 2023-01-01 | 2022-01-01 | 2023-02-01 |  |  |  | On Time | Late End | 2 | 15.38% | 15.38% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=13 | bar: 1 to 1
Job 29 | WP2 | 4.1 | Module 36 | APP2 | KSG | KSG286 | 5: 0; 6: 0; 7: 0; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1 |  | 22.BAR | 1.41 | 7 | 2021-05-01 | 2021-11-01 | 2021-08-01 | 2022-03-01 |  |  |  | Late Start | Late End | 10 | 100% | 142.9% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=12
Job 30 | WP2 | 4.1 | Module 37 | APP1 | BAT | CNN447 | 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1 |  | 22.BAR | 1.91 | 12 | 2021-05-01 | 2021-11-01 | 2021-07-01 | 2022-07-01 | 2021-07-01 |  |  | Late Start | Late End | 10 | 66.67% | 83.33% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=11
Job 31 | WP2 | 4.1 | Module 38 | APP1 | BAT | CNN447 | 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1 |  | 22.BAR | 2.65 | 12 | 2021-05-01 | 2021-11-01 | 2021-07-01 | 2022-07-01 | 2021-07-01 |  |  | Late Start | Late End | 10 | 66.67% | 83.33% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=10
Job 32 | WP2 | 4.1 | Module 39 | APP3 | DDU | DDU209 | 5: 0; 6: 0; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 02.PCW | 3 | 9 | 2021-05-01 | 2021-11-01 | 2021-07-01 | 2022-04-01 | 2021-07-01 |  |  | Late Start | Late End | 10 | 88.89% | 111.1% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=9
Job 33 | WP2 | 4.2 | Module 40 | APP2 | BAT | BAT587 | 8: 0; 9: 0; 10: 0; 11: 0; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 06.FZB | 11 | 16 | 2020-08-01 | 2021-07-01 | 2020-12-01 | 2022-01-01 | 2020-12-01 | 2021-11-17 | Ongoing | Late Start | Late End | 19 | 93.75% | 118.8% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=8
Job 34 | WP2 | 4.2 | Module 41 | APP2 | KSG | KSG286 | 11: 0; 12: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0; 1: 1; 2: 1; 3: 1; 4: 1 |  | 04.NBC | 3 | 4 | 2020-11-01 | 2021-03-01 | 2022-01-01 | 2022-05-01 |  |  |  | Late Start | Late End | 16 | 50% | 400% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=7
Job 35 | WP2 | 4.2 | Module 42 | APP2 | KSG | KSG286 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1 |  | 17.PVT | 6 | 12 | 2021-01-01 | 2022-01-01 | 2021-05-01 | 2022-05-01 | 2021-05-01 |  |  | Late Start | Late End | 14 | 83.33% | 116.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=6
Job 36 | WP2 | 4.2 | Module 43 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 17.PVT | 1 | 12 | 2021-01-01 | 2022-01-01 | 2021-04-01 | 2022-04-01 | 2021-04-01 |  |  | Late Start | Late End | 14 | 91.67% | 116.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=5
Job 37 | WP2 | 4.2 | Module 44 | APP3 | DDU | DDU209 | 5: 0; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 06.FZB | 3.6 | 10 | 2021-05-01 | 2022-02-01 | 2021-07-01 | 2022-04-01 | 2021-06-01 |  |  | Late Start | Late End | 10 | 80% | 100% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=4
| WP2 | 4.3 | Module 45
Job 38 | WP2 | 4.3.1 | Module 46 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1 |  | 16.PCP | 2 | 13 | 2021-01-01 | 2021-10-01 | 2021-05-01 | 2022-06-01 | 2021-05-01 |  |  | Late Start | Late End | 14 | 76.92% | 107.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=2
Job 39 | WP2 | 4.3.1 | Module 47 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1 |  | 17.PVT | 2 | 14 | 2021-01-01 | 2021-10-01 | 2021-04-01 | 2022-06-01 | 2021-04-01 |  |  | Late Start | Late End | 14 | 78.57% | 100% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=1
Job 40 | WP2 | 4.3.2 | Module 48 | APP3 | KSG | KSG839 | [44 empty] | 17.PVT | 10 | 15 | 2021-01-01 | 2022-01-01 | 2021-01-01 | 2022-04-01 | 2021-01-01 |  |  | On Time | Late End | 14 | 93.33% | 93.33% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=0 | bar: 1 to 3
Job 41 | WP2 | 4.3.2 | Module 49 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: s |  | 17.PVT | 2 | 6 | 2021-01-01 | 2021-05-01 | 2021-04-01 | 2021-10-01 | 2021-04-01 | 2021-10-01 | SIGNED | Late Start | Late End | 14 | 183.3% | 233.3% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=1
Job 42 | WP2 | 4.3.2 | Module 50 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1 |  | 04.NBC | 0.66667 | 12 | 2021-01-01 | 2021-04-01 | 2021-04-01 | 2022-04-01 | 2021-04-01 |  |  | Late Start | Late End | 14 | 91.67% | 116.7% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=2
| WP2 | 4.4 | Module 51
| WP2 | T | Module 52 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 6 | 8 | 9 | 12 | 13 | 13 | 12 | 12 | 12 | 14 | 14 | 13 | 7 | 5 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SUBTOTAL | 56.2367 | 167
| WP3 | 5 | Module 53
Job 43 | WP3 | 5 | Module 54 | APP3 | BAT | CNN447 | 7: 0; 8: 0; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1 |  | ERU | 0 | 8 | 2021-07-01 | 2021-10-01 | 2021-09-01 | 2022-05-01 | 2021-09-01 |  |  | Late Start | Late End | 8 | 75% | 100% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=6
Job 44 | WP3 | 5.1 | Module 55 | APP1 | BAT | CNN447 | 11: 0; 12: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1 |  | 20.SCI | 4 | 7 | 2020-11-01 | 2021-01-01 | 2021-05-01 | 2021-12-01 | 2021-05-01 | 2021-11-18 | SIGNED | Late Start | Late End | 16 | 142.9% | 228.6% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=7
Job 45 | WP3 | 5.1 | Module 56 | APP1 | BAT | CNN447 | 12: 0; 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1 |  | 02.PCW | 6 | 8 | 2020-12-01 | 2021-03-01 | 2021-04-01 | 2021-12-01 | 2021-04-01 | 2021-11-18 | Ongoing | Late Start | Late End | 15 | 137.5% | 187.5% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=8
Job 46 | WP3 | 5.1 | Module 57 | APP1 | BAT | CNN447 | 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1 |  | 06.FZB | 6 | 14 | 2021-02-01 | 2021-05-01 | 2021-09-01 | 2022-11-01 |  |  |  | Late Start | Late End | 13 | 42.86% | 92.86% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=9
|  | 5.1 | Module 58
|  | 5.1 | Module 59
| WP3 | T | Module 60 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SUBTOTAL | 16 | 37
| WP3 | 6 | Module 61 | [48 empty] | 0
| WP3 | 6.1 | Module 62 | [48 empty] | 0
| WP3 | 6.2 | Module 63 | [48 empty] | 0
| WP3 | 6.3 | Module 64 | [48 empty] | 0
| WP3 | 6.4 | Module 65 | [48 empty] | 0
| WP3 | T | Module 66 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SUBTOTAL | 0 | 0
Job 47 | WP6 | 7 | Module 67 | APP1 | BAT | CNN447 | 12: 0; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1 |  | COSM | 0 | 5 | 2020-12-01 | 2021-02-01 | 2021-01-01 | 2021-06-01 | 2021-01-01 | 2021-06-01 | Concluded - Report to WP1 pending | Late Start | Late End | 15 | 280% | 300% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=19
Job 48 | WP6 | 7.1 | Module 68 | APP2 | DDU | DDU209 | 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 0; 2: 0 |  | 21.IOS | 25 | 10 | 2021-03-01 | 2022-03-01 | 2021-03-01 | 2022-01-01 | 2021-03-01 | 2022-01-01 | Concluded | On Time | Early End | 12 | 120% | 120% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=20
Job 49 | WP6 | 8 | Module 69 | APP3 | BAT | CNN447 | [44 empty] | ERU | 0 | 4 | 2021-07-01 | 2021-09-01 | 2021-07-01 | 2021-11-01 | 2021-07-01 | 2021-11-01 | Concluded/final report sent to WP1 for uploading | On Time | Late End | 8 | 200% | 200% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=21 | bar: 7 to 10
Job 50 | WP6 | 9 | Module 70 | APP1 | DDU | DDU209 | 12: 0; 1: 0; 2: 0; 3: 0; 4: 0; 6: 0; 7: 0; 8: 0 |  | CRL | 0 | 0 | 2020-12-01 | 2021-04-01 |  |  |  |  | Aborted | Early Start | Early End | 15 | #DIV/0! | #DIV/0! | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=22
Job 51 | WP6 | 9 | Module 71 | APP1 | DDU | DDU384 | 12: 0; 1: 0; 2: 0; 3: 0 |  | PASS | 0 | 0 | 2020-12-01 | 2021-04-01 |  |  |  |  | Aborted | Early Start | Early End | 15 | #DIV/0! | #DIV/0! | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=23
Job 52 | WP6 | 9 | Module 72 | APP1 | BAT | CNN447 | 11: 0; 12: 0; 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1 |  | CRL | 0 | 7 | 2020-11-01 | 2021-06-01 | 2021-04-01 | 2021-11-01 | 2021-04-01 | 2021-11-01 | Concluded - Report to WP1 pending | Late Start | Late End | 16 | 157.1% | 228.6% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=24
| WP6 | 9.1 | Module 73
| WP6 | 9.2 | Module 74
| WP6 | 9.3 | Module 75
Job 53 | WP6 | 10 | Module 76 | APP1 | BAT | CNN447 | 1: 0; 2: 0; 3: 0; 4: 1; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1 |  | COSM | 0 | 7 | 2021-01-01 | 2021-12-01 | 2021-04-01 | 2021-11-01 | 2021-04-01 | 2021-11-01 | Concluded - Report to WP1 pending | Late Start | Early End | 14 | 157.1% | 200% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=28
| WP6 | 10.1 | Module 77
| WP6 | 10.1 | Module 78
| WP6 | 10.1 | Module 79
| WP6 | 10.1 | Module 80
| WP6 | 10.1 | Module 81
| WP6 | 10.1 | Module 82
| WP6 | 11 | Module 83
Job 54 | WP6 | 11.1 | Module 84 | APP1 | KSG | KSG839 | [44 empty] | CHN | 0 | 6 | 2020-06-01 | 2020-12-01 | 2020-06-01 | 2020-12-01 | 2020-06-01 | 2020-12-01 | Concluded/final report sent to WP1 for uploading | On Time | On Time | 21 | 350% | 350% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=36 | bar: 6 to 11
| WP6 | 11.1 | Module 85
| WP6 | 11.1 | Module 86
| WP6 | 11.1 | Module 87
| WP6 | 11.1 | Module 88
| WP6 | 11.1 | Module 89
| WP6 | 11.1 | Module 90
| WP6 | 11.1 | Module 91
| WP6 | 11.1 | Module 92
| WP6 | 11.1 | Module 93
| WP6 | 12 | Module 94
| WP6 | 12.1 | Module 95
| WP6 | 12.2 | Module 96
| WP6 | 12.3 | Module 97
| WP6 | 12.4 | Module 98
| WP6 | 12.5 | Module 99
Job 55 | WP6 | 13 | Module 100 | APP2 | KSG | KSG839 | 10: 0; 11: 0; 12: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1 |  | MLB | 0 | 9 | 2020-10-01 | 2021-05-01 | 2021-05-01 | 2022-02-01 | 2021-05-01 |  | Concluded - Report to WP1 pending | Late Start | Late End | 17 | 111.1% | 188.9% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=52
| WP6 | 13.1 | Module 101
| WP6 | 13.1 | Module 102
| WP6 | 13.1 | Module 103
| WP6 | 13.2 | Module 104
Job 56 | WP6 | 14 | Module 105 | APP2 | KSG | KSG839 | [44 empty] | RMS | 0 | 10 | 2020-10-01 | 2021-05-01 | 2020-10-01 | 2021-08-01 | 2020-10-01 | 2021-08-01 | Concluded - Report to WP1 pending | On Time | Late End | 17 | 170% | 170% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=57 | bar: 10 to 7
Job 57 | WP6 | 14 | Module 106 | APP3 | KSG | KSG286 | 4: 0; 5: 0; 6: 0; 7: 0; 8: 0; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1 |  | MLB | 0 | 10 | 2022-06-01 | 2023-04-01 | 2022-09-01 | 2023-07-01 |  |  |  | Late Start | Late End | 0 | 0% | 0% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=58
Job 58 | WP6 | 14 | Module 107 | APP2 | KSG | KSG839 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1 |  | MLB | 0 | 8 | 2021-01-01 | 2021-07-01 | 2021-05-01 | 2022-01-01 | 2021-05-01 |  | Concluded - Report to WP1 pending | Late Start | Late End | 14 | 125% | 175% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=59
Job 59 | WP6 | 14 | Module 108 | APP3 | KSG | KSG286 | 6: 0; 7: 0; 8: 0; 9: 1; 10: 1; 11: 1; 12: 1; 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1 |  | MLB | 0 | 10 | 2022-06-01 | 2023-04-01 | 2022-09-01 | 2023-07-01 |  |  |  | Late Start | Late End | 0 | 0% | 0% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=60
Job 60 | WP6 | 14 | Module 109 | APP4 | KSG | KSG286 | [44 empty] | CRL | 0 | 6 | 2022-09-01 | 2023-03-01 | 2022-09-01 | 2023-03-01 |  |  |  | On Time | On Time | 0 | 0% | 0% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=61 | bar: 9 to 2
| WP6 | 14.1 | Module 110
| WP6 | 14.2 | Module 111
| WP6 | 14.3 | Module 112
| WP6 | 14.4 | Module 113
| WP6 | 14.5 | Module 114
| WP6 | 14.6 | Module 115
Job 61 | WP6 | 15 | Module 116 | APP2 | KSG | KSG839 | [44 empty] | RMS | 0 | 9 | 2021-02-01 | 2021-08-01 | 2021-02-01 | 2023-01-01 | 2021-02-01 |  |  | On Time | Late End | 13 | 144.4% | 144.4% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=68 | bar: 2 to 7; 10 to 12
| WP6 | 15.1 | Module 117
| WP6 | 15.2 | Module 118
| WP6 | 15.3 | Module 119
| WP7 | 16 | Module 120
| WP7 | 16.1 | Module 121
Job 62 | WP7 | 17 | Module 122 | APP1 | KSG | KSG286 | [44 empty] | 23.PPW | 0 | 12 | 2020-11-01 | 2022-07-01 | 2020-11-01 | 2021-11-01 | 2020-11-01 |  |  | On Time | Early End | 16 | 133.3% | 133.3% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=74 | bar: 6 to 10
Job 63 | WP7 | 17 | Module 123 | APP1 | BAT | BAT587 | [44 empty] | 23.PPW | 0 | 36 | 2020-11-01 | 2023-11-01 | 2020-11-01 | 2023-11-01 | 2020-11-01 |  |  | On Time | On Time | 16 | 44.44% | 44.44% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=75 | bar: 6 to 10
Job 64 | WP7 | 17.1 | Module 124 | APP1 | BAT | BAT587 | [44 empty] | 23.PPW | 0 | 16 | 2020-11-01 | 2022-03-01 | 2020-11-01 | 2022-03-01 | 2020-11-01 |  |  | On Time | On Time | 16 | 100% | 100% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=76 | bar: 11 to 2
Job 65 | WP7 | 17.1 | Module 125 | APP1 | BAT | BAT587 | [44 empty] | 23.PPW | 0 | 20 | 2022-03-01 | 2023-11-01 | 2022-03-01 | 2023-11-01 |  |  |  | On Time | On Time | 0 | 0% | 0% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=77 | bar: 3 to 10
| WP7 | 17.1 | Module 126
| WP7 | 17.2 | Module 127
| WP7 | 18 | Module 128
| WP7 | 18.1 | Module 129
| WP7 | 18.1 | Module 130
| WP7 | 18.2 | Module 131
| WP4 | 19 | Module 132
| WP4 | 19.1 | Module 133
Job 66 | WP4 | 19.1.1 | Module 134 | APP4 | KSG | KSG839 | [44 empty] | 14.EPFL | 12 | 14 | 2022-01-01 | 2023-03-01 | 2022-01-01 | 2023-03-01 |  |  |  | On Time | On Time | 2 | 14.29% | 14.29% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=86 | bar: 1 to 2
Job 67 | WP4 | 19.1.1 | Module 135 | APP4 | KSG | KSG839 | [44 empty] | 02.PCW | 14 | 14 | 2022-01-01 | 2023-03-01 | 2022-01-01 | 2023-03-01 |  |  |  | On Time | On Time | 2 | 14.29% | 14.29% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=87 | bar: 1 to 2
| WP4 | 19.1.2 | Module 136
| WP4 | 19.2 | Module 137
| WP4 | 19.2.1 | Module 138
| WP4 | 19.2.2 | Module 139
| WP4 | 19.3 | Module 140
| WP4 | 19.3.1 | Module 141
| WP4 | 19.3.2 | Module 142
| WP4 | 19.3.3 | Module 143
Job 68 | WP4 | 19.4 | Module 144 | BENCH1 | BENCH1 | BENCH1 | [44 empty] | 10.CEA |  | 9 | 2021-04-01 | 2022-01-01 | 2021-04-01 | 2022-01-01 | 2021-04-01 |  |  | On Time | On Time | 11 | 122.2% | 122.2% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=96 | bar: 4 to 12
Job 69 | WP4 | 19.4.1 | Module 145 | BENCH4 | BENCH4 | BENCH4 | [44 empty] | 13.PHE |  | 4 | 2022-01-01 | 2022-05-01 | 2022-01-01 | 2022-05-01 |  |  |  | On Time | On Time | 2 | 50% | 50% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=97 | bar: 1 to 4
Job 70 | WP4 | 19.4.2 | Module 146 | BENCH2 | BENCH2 | BENCH2 | [44 empty] | 10.CEA |  | 9 | 2021-04-01 | 2022-01-01 | 2021-04-01 | 2022-01-01 | 2021-04-01 |  |  | On Time | On Time | 11 | 122.2% | 122.2% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=98 | bar: 4 to 12
Job 71 | WP4 | 19.4.2 | Module 147 | BENCH3 | BENCH3 | BENCH3 | [44 empty] | 13.PHE | 15 | 15 | 2021-07-01 | 2022-10-01 | 2021-07-01 | 2022-10-01 |  |  |  | On Time | On Time | 8 | 53.33% | 53.33% | https://uc3m-my.sharepoint.com/personal/100391000_alumnos_uc3m_es/Documents/ERA4TB_PBI/Follow-up-fake.docx?web=99 | bar: 7 to 9
| WP4 | 19.4.3 | Module 148
| WP4 | 19.5 | Module 149
Note on AI111: Estefania Callado: 10 months; but postponed start date from Nov21 to around Sept22
Note on M125: Estefania Callado: FSFVisit: 30/10/20 FSFD: 25/11/20
Note on W125: Estefania Callado: SAD/MAD transition on Q3 2021
Note on X125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Finalization of Cohort 3 from the SAD and study transferred to a unit in Cambrige and study funded by GSK in-kind
Note on N127: Estefania Callado: FSFD 1st Dec 2020

## Link to specific APPs
Molecule/APP | Asset Owner | Link to the Specific APP | AMT Meetings
APP1_GSK286 | GSK | Link to APP1_GSK286 (WP7) | Monthly WP7 Meetings (30min)
APP2_GSK286 |  | Link to APP2_GSK286 (WP2) | Monthly WP2 Meetings (1h)
APP3_GSK286 |  | Link to APP3_GSK286 (WP6) | Update regularly by e-mail
APP4_GSK286 |  | Link to APP4_GSK286 (WP6) | Update regularly by e-mail
APP1_GSK839 | GSK | Link to APP1_GSK839 (WP6) | Update regularly by e-mail
APP2_GSK839 |  | Link to APP2_GSK839 (WP6) | Update regularly by e-mail
APP3_GSK839 |  | Link to APP3_GSK839 (WP2) | Monthly WP2 Meetings (1h)
APP4_GSK839 |  | Link to APP4_GSK839 (WP4) | TBD
APP1_TBA587 | TBA | Link to APP1_TBA587 (WP7) | Monthly WP7 Meetings (30min)
APP2_TBA587 |  | Link to APP2_TBA587 (WP2) | Monthly WP2 Meetings (1.5h)
APP3_TBA587 |  | Link to APP3_TBA587 (WP2)
APP1_MPL-447 | TBA | Link to APP1_MPL447 (WP2, 3, 6) | Monthly AWP2 Meetings (1.5h)
APP2_MPL-447 |  | Link to APP2_MPL447 (WP2) | Monthly WP3 Meetings (1.5h)
APP3_MPL-447 |  | Link to APP3_MPL447 (WP3, 6) | Monthly WP6 Meetings (1h)
APP2_DDU209 | DDU | Link to APP2_DDU209 (WP6) | Monthly WP6 Meetings (45h)
APP3_DDU209 |  | Link to APP3 DDU209 (WP2) | Monthly WP2 Meetings (45h)
BENCH1-M19.4-CEA | N/A | Link to BENCH1 CEA | N/A
BENCH2-M19.4.2-CEA |  | Link to BENCH2 CEA | N/A
BENCH3-M19.4.2-PHE |  | Link to BENCH23 CEA | N/A
BENCH4-M19.4.1-PHE
CPP1 | GSK, TBA, DDU | Link to CPP1 | Monthly CPP1 Meetings (1h)
TOTAL: 11h AMT MONTHLY